HLC Steering Committee Meeting Minutes

August 18, 2023

Dominguez Hall, 101P

- 1:05 pm: Meeting was called to order by Justin Gollob.

  - Minutes from May 19, 2023, Steering Committee were approved without objection.

- Website was discussed by Justin Gollob.

  - Website updates are ongoing.  Goal is to provide accurate and up-to-date information to stakeholders.

  - A process was developed so updates to the website will be regular and continuous moving forward.

  - Attendees were shown recent updates to Institutional Research website.

    - Holly will consider advertising these changes to the campus community.

- Dr. Bridge discussed fall activity.

  - HLC site-visit team’s schedule is not locked.

  - Criterion 1-4 are posted on CMU’s MavZone.  Criterion 5 will be posted the week of 8-21-23.

    - Dr. Bridge has received some minor feedback from the faculty on the posted criterion.

  - The goal is to have complete documents ready to read one last time before lock date.  These documents should be available the last week of August.

  - Criterion Chairs were asked to meet with their committees in mid-September.

    - Chairs should reengage with their committees and documents.

    - Chairs should also encourage committee members to attend open-forum meetings.

  - There was a short discussion of how HLC site-visit teams are formed and a general schedule for their visit.

  - Justin Gollob will find a meeting time during the week of 8-25-23 for the next Steering Committee meeting.

  - Please send “Did you Know” submissions to Dr. Bridge by the end of next week (8-21-23).

  - Short discussion on how to handle last minute changes to the structure of IRIS and the name change for WCCC (CMU Tech).

  - Takeaways from the meeting

    - Read criterion one more time.

    - Hold one more criterion committee meeting.

    - Encourage committee members to attend HLC meetings.

Meeting concluded at 1:45 pm.